## Slide 1
Overall project summary and outlook |  |  | G | Project Sponsor: Project Manager: | 
The BT PPM Method approved assets have been migrated along with the assets relating to the BTGS customer delivery operating model. All that now remains is configuring the SharePoint sites to include views and to migrate the hyperlinks across. This is to be completed in the period to the end of September. Issue over handling of pdf files has been resolved. Roll out of the BT project Site continues with feedback being received. Work is starting on scoping v3 of the Project Site template. Planning has started for the knowledge calls and adoption in P&SD. |  |  |  | Report Date: Covers period: | 31/08/2019 10/08/2019 – 30/08/2019
Work package | Team Manager | This week’s achievements |  | Next week’s tasks | 
Migration from Livelink to SP2010 platform | Robert Buttrick supported by Phil Kilford and Paul Riches | Completed |  | Continue prototype build of Approved area and escalation of blockages. | 
Rollout communications and change agenda. | Robert Buttrick | Plan for P&SD specific knowledge calls agreed with Annalee Metcalfe. |  | Continue communications. | 
Develop operational workspaces (Project Site) (Under CAB R4) | Robert Buttrick supported by William Millar | Completed. Now included in on-going communications plan. Meeting held to discuss how to approach version 3. |  | Workshop on v3 capabilities (Ipswich) | 
Project Highlight Report – Knowledge Management / Continuous Improvement
Milestone | Progress |  | Baseline | F’cast
Project site Release 2 ready for launch | Launched on 14 June 2011 | B | 26/5 | 14/6
Architectural solution defined | Prototyping shows that an acceptable architectural approach is possible and an outline has been prototyped | B | 18/4 | 28/6
Approved assets migrated to Livelink | Time slipped pending resolution of design issue by forecast delays are being recovered. | B | 31/5 | 15-30/9
Working areas ready for use by asset owners | Ready for migration. | B | 31/5 | 30/6
Phase 2 project completed | Slippage, being controlled | G | 30/9 | 31/9
ID | Key Issues / Risks | Mitigation Plan | Manager
I 10 | The SP2010 redirector is not working. Duplicates are found | Work around this by having a parallel running period. | 
! 11 | SharePoint cannot handle pdf files | Resolved | 
Key: |  | B | Complete | R | Requires urgent action | A | Needs attention | G | On track
Key actions / decisions required
None required this week.
Project web site link
9